## CONSO PP 2025-2026
PUBLIC BENEFIT ORGANIZATIONS REGULATORY AUTHORITY
CONSOLIDATED PROCUREMENT PLAN I FOR GOODS & SERVICES
FINANCIAL YEAR 2025/2026
No. | Item description | Unit | Qty | Procurement Method | Source of Funds | Estimated cost in Kshs | Time Process | Invite/Advertise Tender | Bid opening | Bid evaluation | Tender award | Notification | Contract Signing | Total time to contract signature | Date for completion of contract
| 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Purchase of motor vehicle/replacement | No | 1 | Framework agreement | GOK | 12000000 | Planned Days | 1.10.2025 | quarter 2 | [5 empty] | 30.06.2026
actual Days
Variance
2 | Telephone Cost & Expenses calling cards | No | 12 | RFQ | GOK | 1500000 | Planned Days | 1.07.2025 | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | 30.06.2026
actual Days
Variance
3 | Google Mail Services | No | 12 | RFQ | GOK | 1925000 | Planned Days | 23.11.2025 | 1.12.2025 | 6.12.2025 | 07.12.2025 | 8.012.2025 | 24.12.2025 | All Quarters | 23.12.2026
actual Days
Variance
4 | Maitainace of Office Equipment furniture & fittings | No | 10 | RFQ/Framework contracts | GOK | 350000 | Planned Days | 1.07.2025 | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | 30.06.2026
actual Days
Variance
5 | Assorted office stationery | No. | Lot | RFQ | GOK | 948800 | Planned Days | 3.1.2026 | 12.1.2026 | 17.1.2026 | 25.1.2026 | 31.1.2026 | 2.2.2026 | 35 days | 3.02.2026
actual Days
Variance
6 | Assorted office toners | Litres | Lots | Framework agreement | GOK | 1170000 | Planned Days
[7 empty] | actual Days | 3.1.2026 | 12.1.2026 | 17.1.2026 | 25.1.2026 | 31.1.2026 | 2.2.2026 | 35 days | 3.02.2026
Variance
7 | Motor Vehicle Maintenance Expenses | No. | Lots | Framework agreement | GOK | 3000000 | Planned Days | 1.07.2025 | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | 30.06.2026
actual Days
Variance
8 | Conference & Workshops | No. | Lot | Framework agreement/RFQ | GOK | 4872000 | Planned Days | 4.10.2025 | 18.10.2025 | 26.10.2025 | 28.10.2025 | 2.11.2025 | 8.11.2025 | 42 days | 2.10.2025
actual Days
Variance
9 | Contracted Cleaning Services | No. | 12 | RFQ | GOK | 2880000 | Planned Days | 21.07.2025 | 28.07.2025 | 10.08.2025 | 14.08.2025 | 18.08.2025 | 26.08.2025 | 36 days | 25.08.2025
actual Days
Variance
10 | Provision of internet services 30/30mb HQRS & 10/10mb for Kisumu, Mombasa, Eldoret & Garissa | No. | 1 | RFQ | GOK | 3120000 | Planned Days | 7.06.2025 | 17.06.2025 | 20.06.2025 | 24.06.2025 | 25.06.2025 | 1.07.2025 | 30 days | 30.06.2025
actual Days
Variance
11 | Medical Insurance | No. | Lot | Open tender | GOK | 20517016 | Planned Days | 14.12.2025 | 29.12.2025 | 15.01.2026 | 25.01.2026 | 10.02.2026 | 24.02.2026 | 30 days | 7.03.2027
actual Days
Variance
12 | GLA Insurance | No. | Lot | Open tender | GOK | 2600000 | Planned Days | 14.12.2025 | 29.12.2025 | 15.01.2026 | 25.01.2026 | 10.02.2026 | 24.02.2026 | 30 days | 7.03.2027
actual Days
Variance
13 | Motor Vehicle Comprehensive Insurance Cover | No. | 8 | RFQ | GOK | 2000000 | Planned | 23.08.2025 | 29.08.2025 | 02.09.2025 | 04.09.2025 | 05.09.2025 | 05.09.2025 | 30 days | 4.09.2026
actual Days
Variance
14 | GPA/WIBA Insurance | No. | Lot | Open tender | GOK | 450000 | Planned Days | 14.12.2025 | 29.12.2025 | 15.01.2026 | 25.01.2026 | 10.02.2026 | 24.02.2026 | 30 days | 7.03.2027
actual Days
Variance
15 | Anti- Virus Security Licences | No. | 105 | RFQ | GOK | 287500 | Planned Days | 2.02.2026 | 9.02.2026 | 16.02.2026 | 23.02.2026 | 2.03.2026 | 9.03.2026 | 30 days | 13.03.2027
actual Days
Variance
16 | Foreign/Local Travel air tickets | No. | Lot | RFQ | GOK | 2000000 | Planned Days | 1.07.2025 | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | 30.06.2026
actual Days
Variance
17 | Upgrade Server Software | No. | Lot | RFQ | GOK | 1000000 | Planned Days | 1.07.2025 | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | 30.06.2026
actual Days
Variance
18 | ICT maintainance contracts server | No. | Lot | RFQ | GOK | 300000 | Planned Days | 1.07.2025 | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | 30.06.2026
actual Days
Variance
19 | Provision of Legal Services | No. | Lot | RFP | GOK | 5000000 | Planned Days | 1.07.2025 | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | 30.06.2026
actual Days
Variance
20 | Purchase of office furniture | No. | Lot | RFQ | GOK | 2300000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
21 | Renewal of Firewall Infrastructure & Licenses | No. | 4 | Open tender | GOK | 3500000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
22 | Printers Maintenance-HQ & Branches (SLA) | No. | 4 | RFQ | GOK | 512000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
23 | Provision of branding services | No. | Lot | RFQ | GOK | 2814022 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
24 | Maintainance Air conditioner | No. | Lot | RFQ | GOK | 150000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
25 | Purchase of Printer | No. | Lot | RFQ | GOK | 300000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
Actual Days
Variance
Variance
26 | Purchase of Video Conferencing TV | No. | 1 | RFQ | GOK | 100000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
27 | insurance of ict equipment | No. | 1 | RFQ | GOK | 500000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
28 | Maintainance ICT Hardware | No. | Lot | RFQ | GOK | 500000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
31 | Maintainance of IT network | No. | Lot | RFQ | GOK | 300000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
32 | Purchase of a Laptop | No. | Lot | RFQ | GOK | 250000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
33 | Maintainance of UPS | No. | Lot | RFQ | GOK | 100000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
34 | Customized Forms | No. | Lot | RFQ | GOK | 651200 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
35 | Printing of Letterheads | No. | Lot | RFQ | GOK | 600000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
36 | Printing of IEC materials & branding services | No. | Lot | RFQ | GOK | 2000000 | Planned Days | 18.10.2025 | 25.10.2025 | 2025-03-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 | 17 days | 30/11/2025
actual Days
Variance
|  |  | TOTAL AMOUNT |  |  | 80097538
| Prepared by: | Accounting Officer: |  |  |  | Sign ……………………………………… Date ……………………………….
Approved by: Cabinet Secretary / CECM / Board / Council: Sign ………………………………………. Date ………………………………
Guidance notes on preparing the procurement plan as per column: -
a) Total value of procurements planned by the entity for the financial year is Kshs. 80,097,538.00
b) Aggregate contracts value set aside for the 30% target groups (Youth, Women and PWD). is Kshs. 24,149,261.40
c) Percentages set aside for the PWD.2% is Kshs.482,985.23
d) Percentages set aside for the local promotion schemes.40% is kshs. 32,199,015.20

## 30% PP FY 2025-2026
AMMENDEND PROCUREMENT 1 PUBLIC BENEFITS ORGANIZATIONS REGURATORY AUTHORITY
PART OF PROCUREMENT PLAN FOR GOODS & SERVICES
|  | FINANCIAL YEAR: |  |  |  | 2025-2026
Part of the Annual Procurement Plan demonstrating application of the Preference and Reservation {Sec. 44(2)(I) & 158(2)}
This Plan must be submitted to the Authority within sixty (60) days after commencement of the financial year i.e. 31st August 2025
No. | Item description | Unit | Qty | Procurement Method | Source of Funds | Estimated cost in Kshs | Time Process | Invite/Advertise Tender | Bid opening | Bid evaluation | Tender award | Notification | Contract Signing | Total time to contract signature | Date for completion of contract
| 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Telephone Cost & Expenses calling cards | No | 12 | RFQ | GOK | 1500000 | Planned Days | 1.07.2025 | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | 30.6.2026
actual Days
Variance
2 | Google Mail Services | No | 12 | RFQ | GOK | 1925000 | Planned Days | 23.11.2025 | 1.12.2025 | 6.12.2025 | 07.12.2025 | 8.012.2025 | 24.12.2025 | All Quarters | 23.12.2026
actual Days
Variance
3 | Provision of printing/branding services | No | Lot | RFQ/Framework contracts | GOK | 4814022 | Planned Days | 1.07.2025 | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | 30.06.2026
actual Days
Variance
4 | Assorted Stationery | No. | Lot | RFQ | GOK | 948800 | Planned Days | 3.1.2026 | 12.1.2026 | 17.1.2026 | 25.1.2026 | 31.1.2026 | 2.2.2026 | 35 days | 3.02.2026
actual Days
Variance
5 | Renewal of Firewall Infrastructure & Licenses | Lot | Lots | RFQ | GOK | 512000 | Planned Days | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters
actual Days
Variance
6 | Purchase of Video Conferencing TV | No. | 1 | RFQ | GOK | 100000 | Planned Days | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters
actual Days
Variance
7 | Telephone Cost & Expenses calling cards | No. | 12 | RFQ | GOK | 1500000 | Planned Days | 4.10.2025 | 18.10.2025 | 26.10.2025 | 28.10.2025 | 2.11.2025 | 8.11.2025 | 42 days | 30.06.2026
actual Days
Variance
8 | Contracted Cleaning Services | No. | 12 | RFQ | GOK | 2880000 | Planned Days | 21.07.2025 | 28.07.2025 | 10.08.2025 | 14.08.2025 | 18.08.2025 | 26.08.2025 | 36 days | 25.08.2025
actual Days
Variance
9 | Renewal of Firewall Infrastructure & Licenses | No. | 1 | RFQ | GOK | 3500000 | Planned Days | 7.06.2025 | 17.06.2025 | 20.06.2025 | 24.06.2025 | 25.06.2025 | 1.07.2025 | 30 days | 30.06.2025
actual Days
Variance
10 | Steel File cabinet | No. | 1 | RFQ | GOK | 400000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
11 | Anti- Virus Security Licences | No. | 105 | RFQ | GOK | 287500 | Planned Days | 2.02.2026 | 9.02.2026 | 16.02.2026 | 23.02.2026 | 2.03.2026 | 9.03.2026 | 30 days | 13.03.2027
actual Days
Variance
12 | Foreign/Local Travel Tickets | No. | Lot | RFQ | GOK | 2000000 | Planned Days | 1.07.2025 | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | All Quarters | 30.06.2026
actual Days
Variance
13 | Purchase of office furniture | No. | Lot | RFQ | GOK | 2000000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
14 | Assorted office toners | Litres | Lots | Framework agreement | GOK | 1170000 | Planned Days
[7 empty] | actual Days | 3.1.2026 | 12.1.2026 | 17.1.2026 | 25.1.2026 | 31.1.2026 | 2.2.2026 | 35 days | 3.02.2026
Variance
15 | Maintainance Air conditioner | No. | Lot | RFQ | GOK | 150000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
16 | Purchase of Printer | No. | Lot | RFQ | GOK | 300000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
Actual Days
Variance
17 | Purchase of a Laptop | No. | Lot | RFQ | GOK | 250000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
18 | Maintainance of UPS | No. | Lot | RFQ | GOK | 100000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
19 | Customized Forms | No. | Lot | RFQ | GOK | 651200 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
20 | Printing of Letterheads | No. | Lot | RFQ | GOK | 600000 | Planned Days | 18.03.2026 | 25.03.2026 | 2026-03-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 17 days | 15.06.2026
actual Days
Variance
Kshs. 24,149,261.40
Guidance notes on preparing the procurement plan as per column: -
a) Total value of procurements planned by the entity for the financial year is Kshs. 80,097,538.00
b) Aggregate contracts value set aside for the 30% target groups (Youth, Women and PWD). is Kshs. 24,149,261.40
c) Percentages set aside for the reservation schemes.16% is Kshs.12,815,606.08
d) Percentages set aside for the local promotion schemes.40% is kshs. 32,199,015.20